## Stakeholder Analysis
STAKEHOLDER ANALYSIS MORTGAGE
Reinventing Mortgage in a transparent and understandable way | [12 empty] | 14.10.2019
NAME OR GROUP | ROLE | PREDISPOSITION |  |  |  |  | ANTICIPATED INVOLVEMENT | ANTICIPATED ISSUES | MOTIVATION / DRIVERS | EXPECTED PAIN POINTS | EXPECTATIONS OF EXCHANGE | MILESTONES | ACTIVITIES
Sponsors, managers, users, etc. |  | Current commitment profile: resistant, ambivalent, neutral, supportive/committed |  |  |  |  | What level of involvement is expected? | Known or potential issues | Why is the stakeholder invested in the project? | What could be improved in the mortgage ecosystem? | What is the stakeholder's predicted input? | At what point in the change effort is this stakeholder's involvement required? | What activities directly involve or impact the stakeholder?
|  |  | - | 0 | + | ++ | very high - high - middle - low - none
Potential Customers | Prospect (without mortgage, considering one) | supportive |  |  |  | ++ | Very high | Low interest and knowledge level | Expected to get benefits from the project | Transparency, Clarity, why should i buy? | Needs / Problems | Preliminary Research | Interviews
Real Estate Agencies | Distribution (Goods) | neutral |  | 0 |  |  | high | Low interest ? | Expected to get positive side effects from the project | Image, Processes and Speed | Needs / Problems | Conception | Interviews
Construction Companies | Distribution (Goods) | neutral |  | 0 |  |  | low | Low interest ? | Expected to get positive side effects from the project | Communication and Amounts of contracts | Needs / Problems | Conception | Interviews
Customers | Customers (with mortgage or sure to get one soon) | supportive |  |  |  | ++ | Very high | Interest conflicts with mortgage Issuers ? | Expected to get benefits from the project | Transparency, Clarity, Speed, Processes, Documentationand administrative workload | Needs / Problems | Preliminary Research | Interviews
Banks | Mortgage Issuers | resistant | - |  |  |  | high | No interest in more transparency | Wants to keep control | Costs and Benefits | Needs / Problems | Preliminary Research | Interviews
Insurance | Mortgage Issuers | resistant | - |  |  |  | high | No interest in more transparency | Wants to keep control | Costs and Benefits | Needs / Problems | Preliminary Research | Interviews
FINMA | Regulation | neutral |  | 0 |  |  | high | Hard to reach | Wants to keep control | Regulation Control | What has to be aligned with regulation | Preliminary Research | Interviews
Moneypark |  | ambivalent |  |  | +
| Management | committed |  |  |  | ++ | middle | Wants to be updated on a regular basis | Wants toincrease traffic and relevance of Moneypark | Costs and Benefits | Definition To Be state | Preliminary Research | Target and Objective Definitions
| Customer Center | resistant | - |  |  |  | high | Project conflicts with interests / fear of losing the job | Wants to keep As Issituation | Processes and Workload | Information about customers problemsand questions | Conception | Interviews
| Distribution & KAM | resistant | - |  |  |  | middle | Project conflicts with interests / fear of losing the job | Wants to keep As Issituation | Processes and Workload | Information about customers / institutions problems | Conception | Interviews
PREDISPOSITION TOTALS |  |  | 4 | 3 | 1 | 3

## Stakeholder Analysis - MATRIX
STAKEHOLDER ANALYSIS MATRIX
INFLUENCE | 0 | ++
| NEGATIVE SUPPORT / | POSITIVE SUPPORT /
| HIGH INFLUENCE | HIGH INFLUENCE
| COMMIT | LEVERAGE
| NEGATIVE SUPPORT / | POSITIVE SUPPORT /
| MODERATE INFLUENCE | MODERATE INFLUENCE
| INVEST | PLAN
| NEGATIVE SUPPORT / | POSITIVE SUPPORT /
| LOW INFLUENCE | LOW INFLUENCE
| PLAN | MAINTAIN
| - | +
SUPPORT
Potential customers
Real Estate Agencies
Construction companies
Customers
Banks
Insurers
FINMA
Moneypark - Management
Moneypark - Customer Center
Moneypark - Distribution + KAM